## Tabelle1
[23 empty] | Planning Resource Sheet (v1.95) | [12 empty] | Name 1:
[23 empty] | AMEISE Project | [12 empty] | Serhii Kovalenko
Matriculation No. 1:
AMEISE username: |  |  |  | 4tuke-86
Effort Distribution:
Simulation Date: | [10 empty] | Run Number: |  |  |  | 1 | [12 empty] | Effort |  | Project Duration | [5 empty] | Name 2:
[21 empty] | Types of Effort |  |  |  |  | % |  | PM |  | months |  | days |  |  |  | Maksym Kozlov
Project Calculation: | [20 empty] | Management |  |  |  |  | 7 |  | 1.8452 |  | 0.4613 |  | 14 |  |  |  | Matriculation No. 2:
AFP: |  |  |  | 200 | [16 empty] | Specification |  |  |  |  | 10 |  | 2.636 |  | 0.659 |  | 20
LOC: |  |  |  | 9800 | [16 empty] | Design |  |  |  |  | 25 |  | 6.59 |  | 1.6475 |  | 50
Est. Proj. Duration: |  |  |  | 8.67 |  |  |  |  | Formula: |  |  | 2,5*(PersonMonths)^0,38 | [8 empty] | Coding |  |  |  |  | 27 |  | 7.1172 |  | 1.7793 |  | 54 |  |  |  | Name 3:
Est. Avg. Developers: |  |  |  | 4 |  |  |  |  | Formula: |  |  | PersonMonths/Duration | [8 empty] | Testing |  |  |  |  | 18 |  | 4.7448 |  | 1.1862 |  | 36
Est. PersonMonths: |  |  |  | 26.36 |  |  |  |  | Formula: |  |  | 2,4*(KLOC)^1,05 | [8 empty] | Reviews |  |  |  |  | 3 |  | 0.7908 |  | 0.1977 |  | 6 |  |  |  | Matriculation No. 3:
[21 empty] | Manuals |  |  |  |  | 10 |  | 2.636 |  | 0.659 |  | 20
Project Schedule: | [20 empty] | Total Effort |  |  |  |  | 100 |  | 26.36 |  | 6.59 |  | 200
Additional Information:
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Customer
[33 empty] | TA | TA | TA | TA | TA | TA | TA | TA
Axel | [14 empty] | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS
Bernd | [29 empty] | R | R | R
Christine |  |  |  |  | SD | SD |  |  |  | CMD | [22 empty] | TM | TM | TM | TM | TM | TM | TM | TM
Diana | [10 empty] | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | [11 empty] | TI | TI | TI | TI | TI | TI | TI | TI
Richard | SP | SP | RSP | CSP |  |  | MD | MD | MD | RSD
Stefanie | [19 empty] | MN | MN | MN | MN | MN | MN | MN | MN | MN | MN
Thomas
Cost Estimation: | [32 empty] | Abreviations (Artefacts/Tasks):
|  | Salary(h) |  |  |  |  | Weeks |  |  |  |  | Months |  |  |  |  | Working Hours |  |  |  |  | Salary (total) | [10 empty] | CD | … | Code
Axel |  | 40 | [30 empty] | MD | … | Module Design
Bernd |  | 40 | [30 empty] | MN | … | Manuals/Documentation
Christine |  | 45 | [30 empty] | SD | … | System Design
Diana |  | 40 | [30 empty] | SP | … | Specification
Richard |  | 50 | [30 empty] | C | … | Correcting (eg. CSP … Correct Specificaton)
Stefanie |  | 40 | [30 empty] | R | … | Review (eg. RSP … Review Specification)
Thomas |  | 45 | [30 empty] | TA | … | Acceptance Test
[33 empty] | TI | … | Integration Test
Additional Costs (which ones?): | [32 empty] | TM | … | Module Test
Total Project Costs: | [21 empty] | 225000 | [10 empty] | TS | … | System Test