## Tabelle1
[23 empty] | Planning Resource Sheet (v1.95) | [12 empty] | Name 1:
AMEISE Project
Matriculation No. 1:
AMEISE username:
Effort Distribution:
Simulation Date: | [10 empty] | Run Number: | [16 empty] | Effort |  | Project Duration | [5 empty] | Name 2:
[21 empty] | Types of Effort |  |  |  |  | % |  | PM |  | months |  | days
Project Calculation: | [20 empty] | Management |  |  |  |  | 7 |  | 1.8452 |  | 0.6069 |  | 18.45 |  |  |  | Matriculation No. 2:
AFP: |  |  |  | 200 | [16 empty] | Specification |  |  |  |  | 10 |  | 2.636 |  | 0.867 |  | 26.36
LOC: |  |  |  | 9800 | [16 empty] | Design |  |  |  |  | 27 |  | 7.1172 |  | 2.3409 |  | 71.16
Est. Proj. Duration: | 8.67 | [7 empty] | Formula: | [11 empty] | Coding |  |  |  |  | 26 |  | 6.8536 |  | 2.2542 |  | 68.53 |  |  |  | Name 3:
Est. Avg. Developers: | 3.04 | [7 empty] | Formula: | [11 empty] | Testing |  |  |  |  | 18 |  | 4.7448 |  | 1.5606 |  | 47.44
Est. PersonMonths: | 26.36 | [7 empty] | Formula: | [11 empty] | Reviews |  |  |  |  | 3 |  | 0.7908 |  | 0.2601 |  | 7.91 |  |  |  | Matriculation No. 3:
[21 empty] | Manuals |  |  |  |  | 9 |  | 2.3724 |  | 0.7803 |  | 23.72
Project Schedule: | [20 empty] | Total Effort
[21 empty] | Total Effort | [6 empty] | 26.36 |  | 8.67 |  | 264 | [7 empty] | Additional Information:
Week | 1
Customer | [32 empty] | TA | TA | TA | TA | TA | TA | TA
Axel |  |  |  | RSP | [6 empty] | CD+RMD | CD | CD | CD | CD | CD | CD | [9 empty] | RTM |  |  |  |  | TS | TS | TS+RTS
Bernd | [8 empty] | CD | CD | CD | CD | CD | CD | CD | CD | [12 empty] | R | R | R
Christine |  |  |  |  | SD | SD | SD | CSD | CSD | [8 empty] | TM | TM | TM | TM | TM | TM
Diana | [7 empty] | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD
Richard | SP | SP | SP | SP |  | MD | MD | MD | MD | MD+RSD | [6 empty] | RCD |  |  |  |  | RTI
Stefanie | [23 empty] | MN | MN | MN | MN | MN | MN | MN | MN | MN | MN
Thomas | [23 empty] | TI | TI | TI | TI | TI | TI+RTI
Cost Estimation: | [32 empty] | Abreviations (Artefacts/Tasks):
|  | Salary(h) |  |  |  |  | Weeks |  |  |  |  | Months |  |  |  |  | Working Hours |  |  |  |  | Salary (total) | [10 empty] | CD | … | Code
Axel | 40 | 19200 | [30 empty] | MD | … | Module Design
Bernd | 40 | 17600 | [30 empty] | MN | … | Manuals/Documentation
Christine | 45 | 19800 | [30 empty] | SD | … | System Design
Diana | 40 | 16000 | [30 empty] | SP | … | Specification
Richard | 50 | 22000 | [30 empty] | C | … | Correcting (eg. CSP … Correct Specificaton)
Stefanie | 40 | 16000 | [30 empty] | R | … | Review (eg. RSP … Review Specification)
Thomas | 45 | 10800 | [30 empty] | TA | … | Acceptance Test
[33 empty] | TI | … | Integration Test
Additional Costs (which ones?): | [32 empty] | TM | … | Module Test
Total Project Costs: |  |  |  |  | 121400 | [27 empty] | TS | … | System Test