## Schedule
Person | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
Customer | bar: W33 to W39
Richard | W1: SP; W2: SP; W3: SP; W4: SP; W6: MD; W7: MD; W8: MD; W9: MD; W10: MD+RSD; W20: RCD; W25: RTI
Christine | W5: SD; W6: SD; W7: SD; W8: CSD; W9: CSD; W18: TM; W19: TM; W20: TM; W21: TM; W22: TM; W23: TM+RTM
Diana | bar: W8 to W17
Axel | W4: RSP; W11: CD+RMD; W12: CD; W13: CD; W14: CD; W15: CD; W16: CD; W17: CD; W30: TS; W31: TS; W32: TS+RTS
Bernd | bar: W9 to W16; W29 to W31
Thomas | W24: TI; W25: TI; W26: TI; W27: TI; W28: TI; W29: TI+RTI
Stefanie | bar: W24 to W33

## Cost Estimation
Person | HourlyRateEUR | PlannedHours | PlannedWeeks(=Hours/40) | PlannedCostEUR | Notes
Richard | 50 | 1242.9 | 31.07 | 62145 | Mgmt+SP+MD+reviews; management overhead included
Christine | 45 | 1049.5 | 26.24 | 47227.5 | SD+CSD+TM
Diana | 40 | 596 | 14.9 | 23840 | Coding primary
Axel | 40 | 628.3 | 15.71 | 25132 | Coding support + System Test + reviews
Bernd | 40 | 366.8 | 9.17 | 14672 | Coding support + reviews
Thomas | 45 | 289 | 7.23 | 13005 | Integration Test lead
Stefanie | 40 | 412.5 | 10.31 | 16500 | Manuals/Documentation
TOTAL |  | 4585 | 114.63 | 202521.5 | Sum of all planned hours and costs
BUDGET_CAP (auto) |  |  |  | 225000 | As provided
BUDGET_SLACK (auto) |  |  |  |  | Budget remaining = Cap - Total

## OptionA
Metric | Value
Person-Months (PM) | 26.36
Duration (months) | 8.67
Duration (days) | 263.57
Avg Developers | 3.04
Category | Percent | PM | Months | Days
Management | 0.07 | 1.8452 | 0.6069 | 18.48
Specification | 0.1 | 2.636 | 0.867 | 26.36
Design | 0.27 | 7.1172 | 2.3409 | 71.16
Coding | 0.26 | 6.8536 | 2.2542 | 68.53
Testing | 0.18 | 4.7448 | 1.5606 | 47.06
Reviews | 0.03 | 0.7908 | 0.2601 | 7.91
Manuals | 0.09 | 2.3724 | 0.7803 | 23.53
TOTAL | 1 | 26.36 | 8.67 | 263.57